## Slide 1: Operational Assessment Boston Public Health Commission
April 2018

## Slide 2: Timeline and Overview
Timeline:
  EY Phase 1: began in March 2017 and concluded in November 2017
  EY Phase 2: began December 2017 – ongoing
  EY Phase 3: kick off April 2018
Phase 1 Scope: Accounting and Finance, Information Technology, Privacy, Property, EMS, Homeless, Recovery
Included processes and internal controls over the following areas:
  Financial: Internal Controls, Post Awards Grants, Budgeting, Billing and AR Management, Procurement and Accounts Payable, and HR/Payroll
  Information Technology
  Privacy and Security
  Facilities and property management
  Inventory Management
  Controlled Substances

## Slide 3: Phase 1 Key Findings (#86)
Financial:
  Process and internal controls over financial reporting
  Grants billing and reporting
  Accounts Payable processing, internal controls and segregation of duties
  Patient billing, collections and denials management: EMS and Bureaus
Controlled Substances:
  Documentation and internal controls over controlled substance inventory at EMS and Homeless Services, and Recovery Services
IT:
  Outdated Information Technology (infrastructure and software)
Privacy and Security:
  Privacy and HIPAA compliance and internal controls (protection of PHI and PII)
Facilities and property management:
  Facilities management and maintenance of properties
Inventory management:
  Physical access controls to drug and non-drug inventories
HR:
  System access and controls to monitor access for terminated employees

## Slide 4: Progress to Date
All findings related to controlled substances were remediated before the end of the assessment.
  Many other findings were also remediated prior to the completion of the assessment.
  Evidence to support the corrective actions were provided to the Assessment Team.
An Action Tracker has been developed and a process to monitor all key findings has been developed.
  Executive Owners have been identified for all issues
  Management responses with specific action plan owners, including the expected date of implementation, have been documented
Remediation plans will be tracked until fully implemented.

## Slide 5: Next Steps
Updates to:
  Internal stakeholders:
    City Hall: HHS, Mayor’s Office, OBM, Press, IGR
    Internal BPHC programs:
    a. Staff from BPHC programs that were covered by operational review: A&F, EMS, Homeless, Recovery Services, General Counsel, ITS.
    b. Board of Health
    c. BPHC Senior Leadership Team
    d. BPHC Program Directors
  External stakeholders: City Council and Boston delegation; DPH (OEMS licensing body for emergency medical services; BSAS – funder and enforcement of substance addictions activities); DHCD (funder of BPHC Homeless Service programs).
EY presentation of operational review on April 11, 2018, Board Meeting

## Slide 6: Next Steps
Convene an Advisory Group to guide remediation activities
  Chair: Manny Lopes * BPHC Board Member
  SMEs:
    Third Party Billing
    IT
    Facilities/Property
    Pharmacy Inventory Management
Provide periodic updates to the BPHC Board and other key stakeholders